PRE-DESIGN

SITE CONSTRAINT ANALYSIS

Run This Before Your Architect Draws a Single Line

| Property Address: |  |
| --- | --- |

Based on lessons learned from 595 Morey Drive, Menlo Park

3-year permit delay  |  $800K+ holding costs  |  5 systemic failures identified

SVDen Development  •  California GC License #B-1049430

# Project Information

Property Address: _______________________________________________

APN (Assessor Parcel Number): _______________________________________________

Lot Size (SF): _______________________________________________

Lot Shape/Configuration: _______________________________________________

Current Zoning Designation: _______________________________________________

General Plan Land Use: _______________________________________________

Overlay Districts: _______________________________________________

Target Use (SFR / MF / Hotel / Mixed): _______________________________________________

Target Gross SF (above grade): _______________________________________________

Target Basement SF: _______________________________________________

Target ADU SF: _______________________________________________

Total Project SF: _______________________________________________

Number of Stories: _______________________________________________

Analyst Name: _______________________________________________

Date of Analysis: _______________________________________________

Sources Reviewed: _______________________________________________

⚠ STOP: Do not proceed to design until every section of this template has a status of CLEAR or MITIGATED. Any FATAL FLAW stops the project.

## How to Use This Template

Complete each section in order. Sections 1–4 should be completed within the first 4 hours of site evaluation. If any section reveals a fatal flaw, stop and evaluate whether the project is viable before investing in design. Each section includes checkboxes, fill-in fields, and a status determination. The template is designed to surface every constraint that caused delays at 595 Morey Drive before a single design dollar is spent.

| Status | Meaning |
| --- | --- |
| ✅ CLEAR | No constraints found. Proceed to next section. |
| ⚠ MITIGATED | Constraint exists but has a clear, documented path to resolution. Note the mitigation strategy. |
| ❌ FATAL FLAW | Constraint that cannot be resolved or makes the project economically unviable. STOP. |

# Section 1: Title & Easement Analysis

MOREY LESSON: At 595 Morey, the 10-foot PUEs on both sides of a pie-shaped lot were not identified until 18 months and 4 revisions into plan check. This single oversight invalidated the entire design and added 7+ months of delay.

## 1.1  Preliminary Title Report Review

Order a preliminary title report (PTR) from a title company before any design work begins. Review every exception listed in Schedule B.

☐ [CRITICAL] Preliminary title report ordered and received

☐ [CRITICAL] All Schedule B exceptions listed and mapped below

☐ Title vested in expected owner / entity

☐ No liens, judgments, or encumbrances that affect development

☐ Property tax status current

Title Company / Order Number: _______________________________________________

Date of PTR: _______________________________________________

Number of Schedule B Exceptions: _______________________________________________

| # | Exception Description | Type | Impact on Buildable Area | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |

## 1.2  Easement Mapping

⚠ CRITICAL: Every easement must be physically drawn on the site plan before design begins. This is the #1 lesson from 595 Morey.

For each easement, identify its type, width, location, and what can/cannot be built within it.

☐ [CRITICAL] All PUEs (Public Utility Easements) identified and mapped

☐ [CRITICAL] PUE widths confirmed with utility providers (PG&E, water, sewer)

☐ All access easements identified and mapped

☐ All drainage easements identified and mapped

☐ All private easements / shared driveway agreements identified

☐ Easement locations confirmed against ALTA survey (not just title report)

☐ Buildable area recalculated AFTER all easements deducted

| Easement Type | Width | Location | Grantor | Build Restrictions | Confirmed By |
| --- | --- | --- | --- | --- | --- |

## 1.3  Buildable Envelope Calculation

After mapping all easements AND setbacks, calculate the actual buildable area. This number—not the lot size—drives the design.

| Constraint | Deduction (SF) |
| --- | --- |
| Total Lot Area |  |
| Front Setback |  |
| Rear Setback |  |
| Left Side Setback |  |
| Right Side Setback |  |
| PUE — Left Side |  |
| PUE — Right Side |  |
| Access Easement(s) |  |
| Drainage Easement(s) |  |
| Other Easement(s) |  |
| BUILDABLE AREA (NET) |  |

Buildable Area as % of Lot: ______ %

Maximum FAR Allowed: ______

Maximum Above-Grade SF (Buildable Area × FAR): ______

Does target project SF fit within buildable envelope? ☐ Yes  ☐ No  ☐ Requires Variance

⚠ If buildable area is less than 50% of lot size on a residential lot, the project is high-risk for design iteration. Consider whether the economics still work.

Section 1 Status: _______________________________________________

Notes / Mitigation Required: _______________________________________________

# Section 2: Zoning & Development Standards

MOREY LESSON: At 595 Morey, the daylight plane violation on the eave overhang was caught by a new planner (Matt Pruter) months after the previous planner (Conner) had indicated approval. Daylight planes, height limits, and setbacks must be verified independently—never rely on a single reviewer’s verbal confirmation.

## 2.1  Zoning District Analysis

☐ [HIGH] Zoning designation confirmed from official zoning map (not Zillow/Redfin)

☐ General Plan consistency verified

☐ Permitted uses confirmed (residential / hotel / mixed-use)

☐ All overlay districts identified (historic, flood, hillside, etc.)

Zoning District: _______________________________________________

General Plan Designation: _______________________________________________

Overlay Districts: _______________________________________________

Approval Pathway (Ministerial / CUP / Design Review / PD): _______________________________________________

## 2.2  Development Standards

| Standard | Code Requirement | Project Proposed |
| --- | --- | --- |
| Max FAR (above grade) |  |  |
| Max Lot Coverage |  |  |
| Max Height (feet) |  |  |
| Max Height (stories) |  |  |
| Front Setback |  |  |
| Rear Setback |  |  |
| Left Side Setback |  |  |
| Right Side Setback |  |  |
| Daylight Plane — Left |  |  |
| Daylight Plane — Right |  |  |
| Daylight Plane — Rear |  |  |
| Min Lot Area per Unit |  |  |
| Parking Required |  |  |
| Basement Exemption from FAR? |  |  |
| ADU Exemption from FAR? (if <800 SF) |  |  |

## 2.3  Daylight Plane Analysis

⚠ CRITICAL: Daylight planes killed the 595 Morey eave design. Verify daylight plane compliance for EVERY wall face and every roof overhang before design proceeds.

☐ [CRITICAL] Daylight plane calculated for all side and rear setbacks

☐ [CRITICAL] Eave overhangs checked against daylight plane on every elevation

☐ Second floor stepped back sufficiently for daylight plane compliance

☐ Roof ridge height verified within daylight plane at all points

Daylight Plane Formula (typically: starts at X ft at setback, rises at Y:Z slope): _______________________________________________

Most Constrained Elevation: _______________________________________________

Maximum Building Height at Most Constrained Point: _______________________________________________

## 2.4  Parking & Access

☐ Required parking spaces calculated

☐ Driveway width meets code (typically 10–12 ft minimum)

☐ Driveway does not conflict with easements or PUE

☐ Guest parking requirement verified

☐ ADU parking requirement (or exemption) verified

Total Parking Required: _______________________________________________

Parking Provided: _______________________________________________

Section 2 Status: _______________________________________________

Notes / Mitigation Required: _______________________________________________

# Section 3: Pre-Application Conference & Multi-Department Review

MOREY LESSON: At 595 Morey, Planning reviewed the design for 18 months without Public Works ever weighing in on the PUE. A single pre-application meeting with all departments present would have surfaced this issue before the first submittal.

## 3.1  Pre-Application Conference

☐ [CRITICAL] Pre-application conference requested with city

☐ [CRITICAL] ALL relevant departments invited: Planning, Public Works, Building, Fire

☐ Written summary of pre-app sent to all attendees for confirmation

☐ All constraints identified in pre-app incorporated into design brief

Pre-App Meeting Date: _______________________________________________

City Staff Present (names and departments): _______________________________________________

Key Issues Identified: _______________________________________________

Follow-Up Actions Required: _______________________________________________

## 3.2  Department-Specific Constraints

| Department | Constraints Identified | Resolution Required |
| --- | --- | --- |
| Planning |  |  |
| Public Works |  |  |
| Building |  |  |
| Fire / Menlo Fire PD |  |  |
| Utilities (PG&E) |  |  |
| Water District |  |  |
| Sanitary (WBSD) |  |  |
| School District |  |  |
| Stormwater / C.3 |  |  |

## 3.3  Staff Continuity Protection

⚠ At 595 Morey, the assigned planner (Conner) left the city. His replacement (Matt Pruter) introduced new comments that the previous planner had not raised. Always document every staff interaction in writing.

☐ [CRITICAL] After every city meeting, send follow-up email summarizing agreements

☐ All staff confirmations documented in writing (not just verbal)

☐ Assigned planner name and contact recorded

☐ Backup contact identified in case of staff turnover

☐ All plan check comments responded to in formal response letter with cross-references

Assigned Planner: _______________________________________________

Assigned Plan Checker: _______________________________________________

Public Works Reviewer: _______________________________________________

## 3.4  Entitlement Vesting Strategy

For projects with extended timelines, consider filing an SB 330 preliminary application (if housing) or requesting a development agreement to vest development standards and prevent mid-review rule changes.

☐ SB 330 applicability evaluated

☐ SB 330 preliminary application filed (if applicable)

☐ Development agreement requested (if applicable for large projects)

☐ Vesting tentative map filed (if subdivision required)

Vesting Strategy Selected: _______________________________________________

Filing Date: _______________________________________________

Section 3 Status: _______________________________________________

Notes / Mitigation Required: _______________________________________________

# Section 4: Physical Site Constraints

MOREY LESSON: 595 Morey is a pie-shaped lot adjacent to a 2-story apartment (privacy concern) and Nealon Park (access easement). Lot shape, adjacencies, and topography directly affect design feasibility and must be documented before design.

## 4.1  Lot Configuration & Adjacencies

☐ Lot shape documented (rectangular, flag, pie-shaped, irregular)

☐ ALTA/ACSM survey ordered or existing survey reviewed

☐ All adjacent property uses documented

☐ Privacy concerns from adjacent properties identified

☐ Noise sources identified (roads, commercial, park, school)

Lot Shape: _______________________________________________

Frontage Width (feet): _______________________________________________

Depth (feet): _______________________________________________

Narrowest Point (feet): _______________________________________________

| Direction | Adjacent Use | Height/Stories | Privacy or Impact Concern |
| --- | --- | --- | --- |
| North |  |  |  |
| South |  |  |  |
| East |  |  |  |
| West |  |  |  |

## 4.2  Topography & Drainage

☐ Site topography reviewed (flat, sloped, hillside)

☐ Drainage patterns identified

☐ Flood zone status checked (FEMA map)

☐ Creek/waterway setbacks identified (if applicable)

Slope (%): _______________________________________________

Flood Zone Designation: _______________________________________________

Drainage Direction: _______________________________________________

## 4.3  Geotechnical

☐ Soil type identified (expansive clay, sand, bedrock, fill)

☐ Liquefaction zone status checked

☐ Landslide zone status checked

☐ Geotech report ordered or scope defined

☐ Foundation type pre-screened (spread footing, mat slab, piers, ICF)

Geotechnical Risk Level: _______________________________________________

Preliminary Foundation Recommendation: _______________________________________________

## 4.4  Utilities

☐ Water service availability and capacity confirmed

☐ Sewer service availability and capacity confirmed

☐ Gas service status (connected / need new connection / demolition required)

☐ Electrical service capacity adequate for project

☐ Utility trenching routes clear of easements

⚠ At 595 Morey, PG&E gas demolition was scheduled for May 2, 2025, while permits were still pending. Confirm utility timelines early to avoid scheduling conflicts.

## 4.5  Environmental & Trees

☐ Heritage/protected trees identified on lot and adjacent lots

☐ Tree survey required? If so, ordered

☐ Environmental contamination screening (Phase I ESA if commercial history)

☐ CEQA pathway determined (Exempt / MND / EIR)

☐ Specific CEQA exemption identified and documented

Number of Protected Trees: _______________________________________________

CEQA Determination: _______________________________________________

Section 4 Status: _______________________________________________

Notes / Mitigation Required: _______________________________________________

# Section 5: Financial & Schedule Constraint Check

MOREY LESSON: At 595 Morey, a bridge loan with a hard maturity date was used to carry the property through a 3-year entitlement process. Holding costs exceeded $800K. The loan nearly defaulted, requiring $56K extension payments and threatening bankruptcy. Never structure financing without entitlement timeline contingency.

## 5.1  Acquisition Financing

☐ [CRITICAL] Loan type appropriate for entitlement timeline (no hard maturity during discretionary review)

☐ Extension options built into loan (minimum 2 extensions)

☐ Monthly holding cost calculated

☐ Maximum hold period before financial distress calculated

Loan Type (Bridge / LOC / Cash / Other): _______________________________________________

Loan Amount: _______________________________________________

Interest Rate: _______________________________________________

Maturity Date: _______________________________________________

Extension Options (number and cost): _______________________________________________

Monthly Holding Cost (P&I + Tax + Insurance): _______________________________________________

Maximum Hold Period Before Distress (months): _______________________________________________

## 5.2  Entitlement Timeline vs. Financing

| Milestone | Estimated Date | Loan Status at Date |
| --- | --- | --- |
| Design Complete |  |  |
| First Plan Check Submittal |  |  |
| Expected Permit Issuance (Best Case) |  |  |
| Expected Permit Issuance (Worst Case) |  |  |
| Construction Loan Closing |  |  |
| Construction Start |  |  |
| Loan Maturity Date |  |  |
| First Extension Deadline |  |  |
| Second Extension Deadline |  |  |

⚠ RED FLAG: If worst-case permit issuance date falls after loan maturity + all extensions, the financing structure is inadequate. Restructure before proceeding.

## 5.3  Fee Estimation

☐ School impact fees calculated ($/SF)

☐ Park / recreation fees estimated

☐ Sewer connection fees confirmed with district

☐ Water connection fees confirmed

☐ Building permit fees estimated from fee schedule

☐ Fire sprinkler permit fees estimated

☐ Planning fees (CUP, design review, etc.) estimated

☐ Total fee burden calculated per unit / per SF

Total Estimated Government Fees: _______________________________________________

## 5.4  Preliminary Pro Forma Check

Before investing in design, verify the project pencils with conservative assumptions. Use worst-case entitlement timeline, +20% construction cost contingency, and -10% on ARV.

Estimated All-In Cost (Acquisition + Holding + Fees + Construction): _______________________________________________

Estimated ARV (After Repair Value) — Conservative: _______________________________________________

Gross Margin: _______________________________________________

Gross Margin %: _______________________________________________

Does it pencil with conservative assumptions?  ☐ Yes  ☐ No  ☐ Marginal: _______________________________________________

Section 5 Status: _______________________________________________

Notes / Mitigation Required: _______________________________________________

# Section 6: Go / No-Go Decision Matrix

Transfer the status from each section into this summary. All sections must be CLEAR or MITIGATED before authorizing design work.

| # | Section | Clear | Mitigated | Fatal | Pending |
| --- | --- | --- | --- | --- | --- |
| 1 | Title & Easements |  |  |  |  |
| 2 | Zoning & Dev Standards |  |  |  |  |
| 3 | Pre-App & Staff Review |  |  |  |  |
| 4 | Physical Site Constraints |  |  |  |  |
| 5 | Financial & Schedule |  |  |  |  |

## Decision

| ☐ GO — Authorize Design All sections CLEAR or MITIGATED. Design brief incorporates all constraints. | ☐ NO-GO — Do Not Proceed One or more FATAL FLAWS identified, or financial constraints unresolvable. |
| --- | --- |

## Design Brief Summary

If GO, summarize the key constraints that must be incorporated into the design brief for the architect:

Maximum Buildable Envelope (SF): _______________________________________________

Maximum Height at Most Constrained Point: _______________________________________________

Easements That Restrict Footprint: _______________________________________________

Daylight Plane Constraints: _______________________________________________

Privacy Mitigation Required: _______________________________________________

Parking Configuration: _______________________________________________

Special Conditions from Pre-App: _______________________________________________

Target Permit Issuance Date: _______________________________________________

Budget Ceiling for Design Phase: _______________________________________________

## Signatures

Site Analyst: ________________________________    Date: ____________

Project Principal: ________________________________    Date: ____________

Reviewed by Counsel (if applicable): ________________________________    Date: ____________

SVDen Development  •  Pre-Design Site Constraint Analysis Template  •  v1.0

Developed from lessons learned at 595 Morey Drive, Menlo Park, CA