PRO FORMA

FINANCIAL DECISION FRAMEWORK

Companion to the Pre-Design Site Constraint Analysis

Does It Pencil? Run the Numbers Before You Spend a Dollar on Design.

Residential  •  Multifamily  •  Hotel  •  Modular

Built from the $800K+ holding cost lesson at 595 Morey Drive, Menlo Park

SVDen Development  •  California GC License #B-1049430

# Financial Decision Framework: How It Works

This framework operates at three levels of increasing detail. Each level is a gate: if the project fails at any level, do not proceed to the next. The goal is to kill bad deals fast and cheap, before investing in design or entitlements.

| Level | Name | Purpose | Time / Cost |
| --- | --- | --- | --- |
| 1 | 5-Minute Napkin Test | Kill obviously bad deals before wasting any time. Back-of-envelope math on ARV, all-in cost, and margin. | 5 minutes / $0 |
| 2 | Development Pro Forma | Line-item cost buildup with timeline, holding costs, financing, fees, and sensitivity analysis. Runs in parallel with Site Constraint Analysis. | 2–4 hours / $0 |
| 3 | Stress Test & Kill Criteria | Break-even analysis, downside scenarios, and explicit kill thresholds. The final gate before authorizing design spend. | 1–2 hours / $0 |

MOREY LESSON: At 595 Morey, a simple holding cost calculation would have shown that a 3-year entitlement timeline on a bridge loan with $15K+/month carrying cost would consume $540K+ before a single nail was driven. The project needed either different financing or a much faster entitlement path to work.

## Decision Rules That Apply Across All Levels

DECISION RULE: Minimum gross margin: 15% for SFR spec, 20% for multifamily, 25% for hotel. Below these thresholds, the risk-adjusted return does not compensate for entitlement, construction, and market risk.

DECISION RULE: Maximum entitlement exposure: Never invest more than 3% of projected total development cost in pre-entitlement soft costs (design, surveys, studies) without a vested entitlement or fallback strategy.

DECISION RULE: Holding cost ceiling: Monthly holding cost (debt service + tax + insurance) must not exceed 1% of expected gross profit. If it does, the timeline must be compressed or financing restructured.

DECISION RULE: Time-value test: Every month of delay costs you the monthly hold PLUS opportunity cost. If a 6-month delay drops IRR below your hurdle rate (typically 15–20% levered), the project fails.

## Project Type Selection

Select the applicable project type below. Each type has different cost assumptions, revenue drivers, and risk thresholds. You may need to run multiple scenarios if the highest-and-best-use is unclear.

| Type | Revenue Driver | Key Cost Variable | Typical Margin |
| --- | --- | --- | --- |
| SFR Spec | ARV (comp-based) | Construction $/SF + holding | 15–25% |
| SFR + ADU (SB 9) | ARV + ADU premium | ADU incremental cost | 20–30% |
| Multifamily | NOI ÷ Cap Rate | Per-unit cost + entitlements | 20–35% |
| Hotel | RevPAR × Keys × 365 | Per-key cost + franchise fees | 25–40% |
| Modular (any type) | Same as base type | Module cost + transport + crane | +3–5% vs conventional |

Selected Project Type for This Analysis: _______________________________________________

# Level 1: The 5-Minute Napkin Test

This is the first financial gate. You should be able to run this test using publicly available data (Zillow, Redfin, county assessor) within 5 minutes. If the deal does not clear this gate, do not proceed to Level 2 or the Site Constraint Analysis.

## 1A. Residential Napkin Test (SFR / SFR+ADU / Multifamily)

| Line Item | Amount |
| --- | --- |
| REVENUE |  |
| A. Estimated ARV (or stabilized value for MF) |  |
| Source: _______ comps at $_______/SF avg |  |
| COSTS |  |
| B. Acquisition (purchase price + closing) |  |
| C. Hard Costs (construction $/SF × total SF) |  |
| Construction $/SF used: $_______ |  |
| Total SF: _______ |  |
| D. Soft Costs (design, engineering, permits = 15–20% of C) |  |
| E. Government Fees (impact + connection + permit) |  |
| F. Holding Costs (monthly hold × months) |  |
| Monthly: $_______ × Months: _______ |  |
| G. Contingency (10% of C+D+E) |  |
| H. Selling Costs (5–6% of A: commissions + transfer tax) |  |
| TOTAL ALL-IN COST (B+C+D+E+F+G+H) |  |
| GROSS PROFIT (A − Total) |  |
| GROSS MARGIN % (Profit ÷ Total) |  |

DECISION RULE: SFR Spec: Gross margin must be ≥15% to proceed. SFR+ADU: ≥20%. Multifamily: ≥20%. If margin is 10–15%, project is marginal—only proceed if you have a clear path to reduce costs or increase value.

## 1B. Hotel Napkin Test

| Line Item | Amount |
| --- | --- |
| REVENUE (Stabilized Annual) |  |
| A. Number of Keys |  |
| B. Average Daily Rate (ADR) |  |
| C. Occupancy Rate (%) |  |
| D. RevPAR (B × C) |  |
| E. Gross Room Revenue (A × D × 365) |  |
| F. Total Revenue (E × 1.25 for F&B + other) |  |
| G. NOI (F × 35–40% margin for select-service) |  |
| VALUATION |  |
| H. Cap Rate (typically 7–9% select-service) |  |
| I. Stabilized Value (G ÷ H) |  |
| COST |  |
| J. Total Development Cost ($/key × keys) |  |
| Cost per key used: $_______ |  |
| DEVELOPMENT SPREAD (I − J) |  |
| YIELD ON COST (G ÷ J) |  |

DECISION RULE: Hotel: Yield on cost must exceed cap rate by ≥1.5% (e.g., 7% cap = need 8.5%+ yield on cost). Development spread must be ≥25% of total cost. If yield on cost is below cap rate, you are destroying value.

## 1C. Napkin Test Decision

| ☐ PASS — Proceed to Level 2 Margin meets threshold. Proceed to detailed pro forma. | ☐ FAIL — Kill or Restructure Below threshold. Either renegotiate acquisition or identify cost reduction. |
| --- | --- |

# Level 2: Development Pro Forma

This is the detailed financial model. Complete this in parallel with the Site Constraint Analysis (Sections 1–4). The constraint analysis tells you what you can build; this tells you what it costs and what it is worth. Every line item requires a source or basis—no guessing.

MOREY LESSON: At 595 Morey, the original pro forma assumed a 12–15 month permit + build timeline. Actual timeline exceeded 36 months. The holding cost alone consumed more than the projected profit margin. Every pro forma must be stress-tested against a realistic worst-case timeline.

## 2A. Sources & Uses of Funds

Uses of Funds (Costs)

| Category | Amount | $/SF | % of Total |
| --- | --- | --- | --- |
| LAND & ACQUISITION |  |  |  |
| Purchase Price |  |  |  |
| Closing Costs (title, escrow, transfer tax) |  |  |  |
| Due Diligence (inspections, surveys, Phase I) |  |  |  |
| TOTAL LAND |  |  |  |
| HARD COSTS |  |  |  |
| Demolition / Site Clearing |  |  |  |
| Excavation & Grading |  |  |  |
| Foundation (or ICF Basement) |  |  |  |
| Structural Framing (wood / steel / CFS / modular) |  |  |  |
| Exterior Envelope (roofing, siding, windows) |  |  |  |
| MEP Rough-In (mechanical, electrical, plumbing) |  |  |  |
| Interior Finishes (drywall, flooring, paint) |  |  |  |
| Cabinetry (Nobilia / other) |  |  |  |
| Appliances |  |  |  |
| Landscaping & Hardscape |  |  |  |
| Fire Sprinkler System |  |  |  |
| ADU (if applicable) |  |  |  |
| Modular Premium / Discount (if applicable) |  |  |  |
| Hard Cost Contingency (10%) |  |  |  |
| TOTAL HARD COSTS |  |  |  |
| SOFT COSTS |  |  |  |
| Architecture & Design |  |  |  |
| Structural Engineering |  |  |  |
| Civil Engineering (grading, drainage, C.3) |  |  |  |
| Geotechnical Report |  |  |  |
| ALTA Survey |  |  |  |
| Title & Escrow (construction) |  |  |  |
| Environmental / CEQA (if applicable) |  |  |  |
| Legal (entitlement, entity, contracts) |  |  |  |
| Accounting / Tax |  |  |  |
| Insurance (builder’s risk + GL) |  |  |  |
| Marketing / Staging / Photography |  |  |  |
| Soft Cost Contingency (5%) |  |  |  |
| TOTAL SOFT COSTS |  |  |  |
| GOVERNMENT FEES |  |  |  |
| Building Permit Fees |  |  |  |
| Planning / Zoning Fees |  |  |  |
| School Impact Fees ($/SF × SF) |  |  |  |
| Park / Recreation Fees |  |  |  |
| Sewer Connection (WBSD or equivalent) |  |  |  |
| Water Connection |  |  |  |
| Fire Sprinkler Permit |  |  |  |
| Other (traffic, art-in-public-places, etc.) |  |  |  |
| TOTAL GOVERNMENT FEES |  |  |  |
| FINANCING COSTS |  |  |  |
| Acquisition Loan Interest (rate × term) |  |  |  |
| Acquisition Loan Points / Origination |  |  |  |
| Construction Loan Interest (draw schedule) |  |  |  |
| Construction Loan Points / Origination |  |  |  |
| Extension Fees (if applicable) |  |  |  |
| Property Tax (during hold period) |  |  |  |
| Property Insurance (during hold period) |  |  |  |
| Utilities (during construction) |  |  |  |
| TOTAL FINANCING / HOLDING COSTS |  |  |  |
| DISPOSITION COSTS (Sale) |  |  |  |
| Broker Commission (2.5–3% per side) |  |  |  |
| Transfer Tax |  |  |  |
| Closing Costs (title, escrow) |  |  |  |
| Home Warranty (if SFR) |  |  |  |
| TOTAL DISPOSITION COSTS |  |  |  |

TOTAL DEVELOPMENT COST (all categories)

## 2B. Revenue Estimation

Residential

| Revenue Component | Amount |
| --- | --- |
| Primary Residence ARV |  |
| Comp 1: _______ at $_______/SF = $_______ |  |
| Comp 2: _______ at $_______/SF = $_______ |  |
| Comp 3: _______ at $_______/SF = $_______ |  |
| Average $/SF: _______ × Project SF: _______ |  |
| ADU Value (if applicable) |  |
| Basement Value Premium (if applicable) |  |
| Premium Features (elevator, Nobilia, smart home) |  |
| TOTAL ESTIMATED SALE PRICE |  |

Hotel

| Revenue Component | Amount |
| --- | --- |
| Rooms Revenue (Keys × ADR × Occ × 365) |  |
| F&B Revenue (typically 15–25% of rooms) |  |
| Other Revenue (parking, events, retail) |  |
| TOTAL GROSS REVENUE |  |
| Less: Operating Expenses (55–65% of revenue) |  |
| Less: Franchise Fees (6–10% of rooms revenue) |  |
| Less: FF&E Reserve (4% of revenue) |  |
| Less: Management Fee (3–4% of revenue) |  |
| NET OPERATING INCOME (NOI) |  |
| Cap Rate for Valuation |  |
| STABILIZED VALUE (NOI ÷ Cap Rate) |  |

## 2C. Returns Summary

| Metric | Base Case | Conservative |
| --- | --- | --- |
| Total Revenue / Sale Price |  |  |
| Total Development Cost |  |  |
| Gross Profit ($) |  |  |
| Gross Margin (%) |  |  |
| Total Equity Invested |  |  |
| Equity Multiple (Profit ÷ Equity) |  |  |
| Total Project Duration (months) |  |  |
| Annualized ROI (Margin ÷ Duration × 12) |  |  |
| Levered IRR (if modeled) |  |  |
| Cash-on-Cash Return |  |  |
| Yield on Cost (Hotel only: NOI ÷ TDC) |  |  |

DECISION RULE: Conservative case: ARV at -10%, construction costs at +20%, timeline at +50%. If the project still meets minimum margin thresholds under conservative assumptions, it is a strong deal.

## 2D. Holding Cost Burn Rate & Timeline Sensitivity

MOREY LESSON: 595 Morey monthly burn: ~$15K (bridge loan interest) + $3K (property tax) + $1K (insurance) = ~$19K/month. Over 36 months of permitting delays: ~$684K consumed before construction started. This section forces you to calculate exactly when the hold kills the deal.

Monthly Holding Cost Breakdown

| Monthly Cost Item | $/Month |
| --- | --- |
| Acquisition Loan Debt Service |  |
| Property Taxes (annual ÷ 12) |  |
| Property Insurance (annual ÷ 12) |  |
| Utilities / Maintenance |  |
| HOA / Assessments (if any) |  |
| TOTAL MONTHLY BURN RATE |  |

Timeline Scenario Analysis

Run the pro forma at three timeline scenarios to see how sensitive the deal is to delays.

| Metric | Best Case | Base Case | Worst Case |
| --- | --- | --- | --- |
| Entitlement Duration (months) |  |  |  |
| Construction Duration (months) |  |  |  |
| Sale / Lease-Up (months) |  |  |  |
| Total Duration (months) |  |  |  |
| Total Holding Cost ($) |  |  |  |
| Gross Profit ($) |  |  |  |
| Gross Margin (%) |  |  |  |
| Annualized ROI (%) |  |  |  |

Break-Even & Death Point Analysis

⚠ The Death Point is the month at which cumulative holding costs consume your entire projected profit. If your worst-case timeline extends past the death point, the deal has unacceptable risk without restructured financing.

| Break-Even Metric | Value |
| --- | --- |
| Projected Gross Profit (base case) |  |
| Monthly Burn Rate |  |
| Death Point Month (Profit ÷ Monthly Burn) |  |
| Loan Maturity Month (from acquisition) |  |
| Loan Maturity + All Extensions |  |
| Worst-Case Total Duration |  |

DECISION RULE: If Death Point Month < Worst-Case Duration: RESTRUCTURE FINANCING before proceeding.

DECISION RULE: If Loan Maturity + Extensions < Worst-Case Permit Timeline: RESTRUCTURE FINANCING before proceeding.

DECISION RULE: Ideal: Death Point should be at least 2× your worst-case total duration. This gives you a margin of safety for the unexpected.

# Level 3: Stress Test & Kill Criteria

This is the final financial gate. Take your base-case pro forma and systematically degrade each assumption. If the project survives the stress test, it is a GO. If any single stress case kills the deal, you must either mitigate that specific risk or walk away.

## 3A. Single-Variable Stress Tests

For each variable below, hold all other assumptions constant and stress only the variable shown. Record the result and determine if the project still meets minimum thresholds.

| Stress Scenario | Base Case | Stressed | Margin % | Pass? |
| --- | --- | --- | --- | --- |
| ARV / Sale Price: -10% |  |  |  |  |
| ARV / Sale Price: -15% |  |  |  |  |
| ARV / Sale Price: -20% |  |  |  |  |
| Hard Costs: +10% |  |  |  |  |
| Hard Costs: +20% |  |  |  |  |
| Hard Costs: +30% |  |  |  |  |
| Timeline: +6 months |  |  |  |  |
| Timeline: +12 months |  |  |  |  |
| Timeline: +18 months |  |  |  |  |
| Interest Rate: +2% |  |  |  |  |
| Occupancy: -10% (hotel) |  |  |  |  |
| ADR: -15% (hotel) |  |  |  |  |

## 3B. Combined Stress Test (Worst Realistic Case)

This is the scenario that actually happens in a downturn: multiple things go wrong simultaneously. Apply ALL of the following at once: ARV -10%, hard costs +20%, timeline +50%.

| Combined Stress Metric | Value |
| --- | --- |
| Stressed Revenue (ARV at -10%) |  |
| Stressed Cost (+20% hard costs) |  |
| Stressed Holding (+50% timeline) |  |
| Stressed Gross Profit |  |
| Stressed Gross Margin % |  |

DECISION RULE: Combined stress test: If gross margin is still positive, the project has a reasonable margin of safety. If margin goes negative under combined stress, the project is a leveraged bet on everything going right. Proceed only if you can absorb the downside.

## 3C. Explicit Kill Criteria

Check each criterion below. Any single KILL triggers a no-go unless the specific risk can be structurally mitigated (not just "managed" or "hoped away").

| Kill Criterion | Kill? | Safe? | N/A |
| --- | --- | --- | --- |
| Base case gross margin < minimum threshold (15% SFR / 20% MF / 25% Hotel) |  |  |  |
| Combined stress test produces negative margin |  |  |  |
| Death point month < worst-case total project duration |  |  |  |
| Loan maturity + extensions < worst-case permit issuance date |  |  |  |
| Monthly burn > 1% of expected gross profit |  |  |  |
| Pre-entitlement soft cost exposure > 3% of total development cost |  |  |  |
| Single point of failure with no mitigation (e.g., sole-source funding, one buyer) |  |  |  |
| Site constraint analysis reveals unresolved FATAL FLAW |  |  |  |
| Conservative ARV requires comps that don’t exist in the market |  |  |  |
| Construction cost estimate has no GC bid or comparable project basis |  |  |  |
| Entitlement path requires discretionary approval with organized opposition |  |  |  |
| Franchise agreement (hotel) requires signing before entitlement certainty |  |  |  |

# Financial Go / No-Go Decision

This is the final financial gate. It integrates with the Site Constraint Analysis decision (Section 6 of the companion template). BOTH must show GO for the project to proceed.

| Gate | Pass | Fail | Conditional |
| --- | --- | --- | --- |
| Level 1: Napkin Test |  |  |  |
| Level 2: Pro Forma (Base Case) |  |  |  |
| Level 2D: Holding Cost / Timeline |  |  |  |
| Level 3A: Single-Variable Stress |  |  |  |
| Level 3B: Combined Stress |  |  |  |
| Level 3C: Kill Criteria (none triggered) |  |  |  |
| Site Constraint Analysis (Sections 1–5) |  |  |  |

## Decision

| ☐ GO All gates pass. Authorize design spend. Transfer constraints to design brief. | ☐ CONDITIONAL One or more conditions must be met before proceeding. Document conditions below. | ☐ NO-GO Kill criteria triggered or combined stress negative. Walk away or renegotiate. |
| --- | --- | --- |

## Conditions (if Conditional GO)

Condition 1: _______________________________________________

Condition 2: _______________________________________________

Condition 3: _______________________________________________

Deadline to Satisfy Conditions: _______________________________________________

Maximum Capital at Risk Before Conditions Met: _______________________________________________

## Key Financial Metrics Summary

| Metric | Value |
| --- | --- |
| Total Development Cost |  |
| Equity Required |  |
| Estimated Sale Price / Stabilized Value |  |
| Gross Profit (Base Case) |  |
| Gross Margin % (Base Case) |  |
| Gross Profit (Conservative) |  |
| Gross Margin % (Conservative) |  |
| Monthly Burn Rate |  |
| Death Point (months) |  |
| Expected Duration (months) |  |
| Annualized ROI (Base Case) |  |
| Equity Multiple |  |

## Signatures

Financial Analyst: ________________________________    Date: ____________

Project Principal: ________________________________    Date: ____________

SVDen Development  •  Pro Forma Financial Decision Framework  •  v1.0

Companion to the Pre-Design Site Constraint Analysis Template